## Slide 1
Risk Appetite Statement – Recalibration Support
Project Kick-off

## Slide 2
Agenda
Timeline & stakeholders
2016 RAS metrics
Tracking strategic risk
Open questions & next steps

## Slide 3
Mar
Apr
May
27.
03.
10.
17.
24.
01.
08.
15.
22.
29.
Prepare full RAS documentation packs
Presentation preparation
Review & refine recalibration with core stakeholders
Collect & verify CCAR results and external data
Recalibrate CCAR-linked financial metrics
Select & calibrate new metrics
Stakeholder socialization
Socialize recalibration with Entity stakeholders
Review board presentations with leadership
Prepare board presentations
Metric recalibration
OW handover to
RAS team
Kick-off
RAS support – Timeline
Project timeline

## Slide 4
Entity | RAS contacts | Senior Stakeholders | Key deadlines
SHUSA | Michael Zhang | Scott Powell (CEO) Brian Gunn (CRO) Duke Dayal (CFO) | May 17th (Leadership review) June 15 (ERMC) June 28 (Risk Cmte.) June 29 (BoD - submit to Legal by June 21)
SBNA | James Vincent | Scott Powell (CEO) Brian Gunn (CRO) | June 15 (ERMC) June 29 (BoD: submit to Legal by June 21)
SCUSA | Michael Bishop | Jason Kulas (CEO) Kalyan Seshan (CRO) Ismail Dawood (CFO) | April 20 (ERMC) May 25 (ERMC) July 28 (BoD)
BSPR (PR) | Dayna Fabricio Juan Pablo Jurado | Juan Sebastián Moreno Blanco (CEO) | June 23 (Risk Cmte.) June 24 (BoD: submit to Legal by June 16)
BSI-Miami | Henry Certain | TBD | Submit to Legal by June 9 June 16 (Risk Cmte.)
SIS (NY) | Michelle Murphy | James Bathon (CRO) | June 24 (BoD: submit to Legal by June 17)
RAS support – Key stakeholders
Are there any additional key stakeholders and how should we involve the stakeholders in the socialization process?

## Slide 5
2015 vs 2016 RAS metrics (1/2)
Risk | Metrics |  | 
Capital adequacy | Common Equity Tier 1 Ratio Tier 1 Risk-based Capital Ratio Tangible Common Equity Ratio Total Capital Ratio Tier 1 Leverage Ratio |  | 
Credit risk | Net charge-off rate %60/61+ days past due CCAR loss budget Counterparties with internal risk rating < 5.0 and exposure > $100 MM |  | 
 | Cost of Credit (calculated through ALLL and charge-offs) NPL entries (%) (TBD) NPL coverage ratio (%) (TBD) Exposure concentrations1 BSI–Miami: Sec. lending exceptions(%), LTV, max exposure (individual & top 10 obligors), non-investment grade collateral / pledged asset (%) |  | 
Residual value risk | Residual value deterioration Net residual value exposure |  | 
Operational risk | Gross operational risk losses/gross margin Frequency: >$200K in losses |  | 
 | Frequency: OR events R1, Fraud, Technology, Cyber Risk, > $50K in losses (Miami) |  | 
CCAR-linked / OW recalibration
New 2016 metrics
Industry, CRE, multifamily, single obligor, top 20 obligors, large exposures, financial institutions (single counterparty & top 20), underwriting (individual transactions & total), specialized lending exposures
Methodology may not be CCAR linked
For Group metrics, do we need to calibrate limits or only report?

## Slide 6
2015 vs 2016 RAS metrics (2/2)
Risk | Metrics | 
Strategic risk (see following slides) | Pre-provisioned net revenue (PPNR) impairment Loss in stress (Credit, Trading, & Op) SCUSA Total Risk Weighted Assets (RWAs) | 
 | SCUSA subprime assets as % of SHUSA total credit exposure Credit exposure over AuM (%) | 
Liquidity / funding risk | Liquidity stress testing survival horizon Available committed liquidity/average projected net originations Liquidity Coverage Ratio Structural Funding Ratio | 
 | Asset encumbrance (%) | 
Interest rate risk | Net interest income sensitivity (+/- 100bps) Market value of equity sensitivity (+/- 200bps) | 
Mark-to-market risk | Mark-to-market Value at Risk (VaR) | 
Model risk | Backlog of Tier 1 models not appropriately approved | 
Compliance & reputational risk | Matters Requiring Immediate Attention (MRIAs) Suitability Review CFPB Complaints Serviced for others monthly net charge-off rate Total new monthly arbitrations and court proceedings Total number of sales practice complaints (monthly) High Risk Customers (% of total customers) | 
Fiduciary risk | Pending purchase order documentation (%) Discretionary mandates: aging of excesses (months) Clients with missing profiles (%) Exceeded client investment profiles (%) | 
CCAR-linked / OW recalibration
New 2016 metrics
Why is this included SCUSA RAS?

## Slide 7
 | SCUSA | SBNA | BSPR | BSI - Miami
CCAR loss budget | Auto Unsecured | Retail Wholesale GBM | TBD | TBD
Net charge-off rate | Auto Unsecured | Retail Small Business/Business Banking/Auto C&I CRE GBM | Mortgages Commercial banking CRE Personal loans Credit cards Institutional | 
%60/61+ days past due | Auto Unsecured | Retail | Mortgages Personal loans Credit cards | 
Segmentation of credit risk metrics
Is this still the correct level of segmentation? Are these still the correct segments (e.g., Unsecured)?
Credit risk segmentation
Do we need this level of detail for PR? CRE is not reported separately, so will need to apply mapping assumptions
Do we still want to segment the Unsecured portfolio?

## Slide 8
Current vision for 2016 strategic risk metrics
“The risk to current or projected financial condition and resilience arising from adverse business decisions, poor implementation of business decisions, or lack of responsiveness to changes in the banking industry and operating environment.”
– OCC, Bank Supervision Process—Comptroller’s Handbook
Quantitative metrics |  |  |  |  |  |  | 
 |  |  | Entity RAS |  |  |  | 
 | Group | SHUSA | SBNA | SC | BSPR* | BSI Miami | SIS
PPNR impairment |  |  |  |  |  |  | 
Loss in stress |  |  |  |  |  |  | 
SCUSA RWA |  |  |  |  |  |  | 
SC subprime / SHUSA credit exposure |  |  |  |  |  |  | 
Credit exposure / AuM |  |  |  |  |  |  | 
Qualitative statements SHUSA will… Strive to deliver constant performance through pragmatic risk-taking Not place an undue amount of earnings or capital at risk for an entity of its size, complexity, and risk profile in any stress scenario Ensure that adequate governance and oversight processes and controls are in place for all business activities, products, and services Consider and work with the risk appetite setting, capital planning, and recovery and resolution planning processes1
1. Recovery and resolution planning process is not applicable to BSPR
* IHC only

## Slide 9
Potential methods for tracking for strategic risk
Quantifying strategic risk | Sample metrics | Comments
Financial-resiliency metrics | PPNR impairment Loss in stress | Legacy and new metrics requested by Group – are these truly strategic risk indicators?
Concentration metrics | SCUSA subprime assets / SHUSA credit exposure (%) Credit exposure / AuM | 
Other capital metrics | Upstream dividends | Provide binary view of Entity ability to upstream cash flows (based on revenue streams and/or regulatory approval)
Plan-based metrics | Project spending Budget tracking | Direct link to the strategic plan and progress against it
Firm ratings | Debt ratings | External assessment of internal performance; potentially duplicative of long term credit ratings currently reported to BoD
External metrics | Macroeconomic factors CDS spreads | Not relevant to strategic plan and not applicable to internal accountability
Current metrics
What is the goal of the strategic risk metrics? How are they differentiated from the goals of strategic planning and Finance? Would this be best captured in a qualitative assessment?

## Slide 10
Potential methods for tracking for strategic risk
Quantifying strategic risk | Sample metrics | Comments
Financial-resiliency metrics | PPNR impairment Loss in stress | Legacy and new metrics requested by Group – are these truly strategic risk indicators?
Concentration metrics | SCUSA subprime assets / SHUSA credit exposure (%) Credit exposure / AuM | 
Other capital metrics | Upstream dividends | Provide binary view of Entity ability to upstream cash flows (based on revenue streams and/or regulatory approval)
Plan-based metrics | Project spending Budget tracking | Direct link to the strategic plan and progress against it
Firm ratings | Debt ratings | External assessment of internal performance; potentially duplicative of long term credit ratings currently reported to BoD
Return-related metrics | ROTE, RORWA Growth Earnings volatility | Incorporating profit/revenue performance metrics may confound and distract from focus on firm’s risk appetite
External metrics | Macroeconomic factors CDS spreads | Not relevant to strategic plan and not applicable to internal accountability
Current metrics
What is the goal of the strategic risk metrics? How are they differentiated from the goals of strategic planning and Finance? Would this be best captured in a qualitative assessment?

## Slide 11
Key open questions
  If the BHC now uses an FRB scenario for baseline, should we rethink use of BHC scenario for calibration?
Additional methodology decisions TBD
Open questions & next steps
Next steps
Gather and update outstanding internal data (historical and CCAR) as available based on timelines
Prepare excel recalibrations
Review outstanding methodology questions
Incorporate strategic planning (latest version available?)
Review list of metrics with John/Sarah to incorporate feedback from Board (has Beatrice already done this?)
Hold weekly updates